## Slide 1
USDA CIO Rating Criteria Overview
Version 1.9 (FINAL)
Naomi Gumbs, Director
Capital Planning and IT Governance Division (CPITGD)
Office of the CIO | Information Resource Management Center (IRMC)
capitalplanningdivision@usda.gov
EFFECTIVE: JUNE 2021

## Slide 2
Table of Contents
History of Changes
Summary of BY2022 Changes
Frequently Asked Questions
Investment Rating Schedule
Detail Scoring Criteria
Appendices

## Slide 3
History of Changes
Version | Date | Summary of changes
1.5 | July 2019 | New and updated BY2021 criteria added.
1.6 | Sept 2019 | Added additional clarification to CIO Rating schedule.
 |  | Corrected link name to reflect IITGF Deliverable Matrix.
 |  | Added clarification for SDLC associated with Post Implementation Review.
 |  | Changed CIO to MA CIO for applicable required signature.
1.7 | Dec 2019 | OVERVIEW: Added PM Assigned to multiple investments criteria
 |  | PERFORMANCE METRICS: Provided additional clarification on MA CIO Approval on Performance metrics. Investment Charter template has been updated to identified Performance metrics which should align with the Performance Metric table in AgMax. Performance Metric (MET?=YES) – Added: If 50%-100% performance metrics have been met – score 3 If less than 50% percent has been met – score 1

## Slide 4
History of Changes
Version | Date | Summary of changes
1.7 | DEC 2019 | PM CERTFICATION: Added to score 1: PM certification is no longer active Recertification date has passed
 |  | CONTRACTS: Add CO/COR FPDS email confirmation to required documentation section
 |  | RISKS: Provided additional clarification on Risk register monthly updates and assessment periods All risk areas identified contains description, mitigation strategy and contingency plan regardless of probability and impact score Reworded criteria to…. Risk Register contains a cross-section of applicable risk areas: (removed the ‘at least 3’). All risk areas should be reviewed and identified if applicable
 |  | IT GOVERNANCE: **Additional requirements pending**
 |  | TBM: **Updates to wording for clarification pending**
1.8 | JUNE 2020 | Edits received from the Frequently Asked Questions (FAQs) for Version 1.7
1.9 | MAR 2021 | V1.9 Released. Edits received from the V1.9 Scoring Criteria Focus Group

## Slide 5
Summary of Changes (Version 1.9)
# | Summary of Changes (Version 1.9) | Status
1 | Investment Overview – Removed Criteria for PMs with Multiple Investments. | Updated
2 | Performance Metrics – Updated verbiage of criteria to provide clarity on reporting frequencies. | Updated
3 | Contracts – Updated verbiage of criteria to provide clarity. | Updated
4 | Risk Management – Updated Risk Register frequency. Also, updated threshold to update “Red” Risk. | Updated
5 | Governance – Update requirements for investment and key projects briefings to applicable Governance Boards (to include the Integrated Advisory Board (IAB) and E-Board). | New
6 | Artifacts – Updated clarity and artifacts (Joint Certification and Inter-Agency Agreement). | Updated
7 | Project Management – Added criteria for incremental/iterative/agile development related to ACIO Performance Requirement #1, Audits and the FITARA Congressional Scorecard. Added clarity for Software Development and O&M projects. | New
8 | TBM – Added criteria for a fourth metric to report “Cost Savings/Cost Avoidance” related with ACIO Performance Requirement #2, Audits and the FITARA Congressional Scorecard. Each Mission Area will be assessed base upon their reported initiatives. No cost is associated with this criteria. You will get credit for existing reporting of CS/CA. | New
Mission Area Feedback Analysis
CIO Rating Criteria Release Dates:
Version 1.7 – Released October 2019 (Automated Scoring Criteria)
Version 1.8 – Released June 2020 (Change in OMB Requirements)
Version 1.9 – Released June 2021 (Mission Area Feedback & FITARA Scorecard)
Focus Group: V1.9 Scoring Criteria Comments

## Slide 6
Frequently Asked Questions (FAQs) are located on the CPITGD SharePoint site.
The FAQs provide additional guidance and any applicable workarounds due to pending enhancements.
Frequently Asked Questions

## Slide 7
Ground Rules
USDA OCIO determines the criteria for Major Investments. The USDA Major Investment determination includes criteria from USDA Major Investment Definition - DR 3130-008 and USDA Major Investment Designation..
To confirm USDA Internal Investment type, run the USDA Major and Non-Major Designation for Investments scorecard.
The Scoring Criteria requirements applies to all investments.
All Standard Investment Reports (SIRs) are required to be completed.
OMB MAJORS AND STANDARDS
  Mission Areas are to update their investments on a monthly basis. Investments are reviewed on a monthly basis by the CPITGD but the CIO Ratings are posted quarterly to the IT Federal Dashboard.
  The quarterly assessment for investments that qualified as an OMB Major investment will be in January, March, June, and September.
OMB NON-MAJORS
  Mission Areas are to update their investments on a monthly basis.
  The semi-annual assessment for OMB Non-Majors investments will occur in May and November.
Funding Transfer Investments - Type 04
  Will receive a score of 3 “Medium Risk” and are not subject to these USDA CIO Rating requirements.
For further guidance refer to:
  OMB FY2022 IT Budget Capital Planning Guidance
  USDA FY2022 IT Budget Capital Planning Guidance Overview & Reference Guide

## Slide 8
Mission Area updates data and Mission Area Assistant CIO Self Assessments
CPITGD distributes initial comments and score to Mission Area staff and leadership
CPITGD facilitates OMB data validation and submission to the Federal IT Dashboard (ITDB) for Major Investments
CPITGD and Mission Areas discuss scoring and adjust based on OCIO leadership review, as needed
USDA’s IT Investment CIO Rating Process supports ongoing partnership and collaboration.
IT Investment CIO Rating Process
Mission Area Updates and Assessment
CPITGD Review and Scoring
Scoring Review and Finalization
OMB Validation and Submission
1st business day: Unlock AgMAX for Updates
11th business day: AgMAX Locked for CPITGD Review
Ongoing: Mission Area & CPITGD engagement and collaboration
Last business day: Complete ITDB Submission
22nd business day: Begin ITDB submission
AgMAX Locked

## Slide 9
Schedule of CIO Rating
Investment Type | CIO Rating Frequency | Investment Data Coverage (*10th business day) | CIO Rating Submission
OMB Major and Standard Investments | Quarterly (Submitted to OCIO & ITDB) | Oct – Dec Jan – Mar Apr – Jun Jul – Sep NOTE: August updates will end prior to the 10th business day in preparation for the OMB Annual submission. | Jan (Passback) Mar Jun Sep (Annual)
OMB Non-Major Investments | Semi-Annually (Submitted to OCIO) | Nov – May May – Nov | May Nov
*Mission Area Assistant CIOs are required to provide a summary assessment of their IT Investment on the CIO Rating form.
**During OMB Annual and Passback submission periods, AARs submissions without DLCC cost modifications will be accepted.
AgMax – Business Case | 
Agency Updates / MA Assistant CIO Assessment* Questions/Coordination with CPITGD Liaison: OMB Majors assessments conducted every Quarter OMB Non-Majors conducted Semi-Annually. | 1st - 10th business day
BUSINESS CASE/DLCC LOCKED** | 11th business day
OCIO/IRMC/CPITGD Assessment, Validation, & Discussions Follow up with Mission Area as needed | 11th – 21st business day
AgMax ITDB submissions (Major Investments) | Begins 22nd business day
BUSINESS CASE/DLCC UNLOCKED | 1ST business day of the month

## Slide 10
This document describes the criteria used by the Office of the Chief Information Office (OCIO) Capital Planning and IT Governance Division (CPITGD) to rate investment business cases and their supporting documentation.
The rating system employs different sets of rating criteria corresponding to different parts of the business case and its supporting documentation. The CIO Rating sections are: Investment Overview, Contract /Acquisition Strategy, Performance Metrics, Risk Management, Project Management, FAC Project/Program Management Certification, Technology Business Management (TBM), and IT Governance (applicable for ALL Investments).
For each set of rating criteria, the range of possible scores in AgMax are 1 to 5. After assigning a score to each area, the individual criteria scores are then weighted to determine an overall numeric score, which then is categorized as green, yellow or red. Scores are not rounded up or down.
Score | Color Assigned | Score (Major CIO Ratings posted to ITDB)
1 | Red | High Risk
2 | Red | Moderately High Risk
3 | Yellow | Medium Risk
4 | Green | Moderately Low Risk
5 | Green | Low Risk
CIO RATING

## Slide 11
Detailed Scoring Criteria

## Slide 12
Scoring Criteria: Investment Overview
Score | 
5 | In addition to meeting the criteria for a rating of 4: All the investment information provided is supported (aligned to the supporting documentation) and enhanced/updated throughout the Investment, Business Case Detail, TBM Reporting, System Inventory and Agency IT Portfolio. Manual Yes/No. Checklist Question: All the investment information provided is supported (aligned to the supporting documentation) and enhanced/updated throughout the Investment, Business Case Detail, TBM Reporting, System Inventory and Agency IT Portfolio AoA for new investments are provided as needed Manual Yes/No/N/A. Checklist question: AA for new initiative(s) have been provided as needed based upon the results of the Operational Analysis AoA includes information resulting from Cost Benefit Analysis (CBA) and address expectations for Return on Investment (ROI). ROI is consistent with the current Alternatives Analysis, Operational Analysis and information in the Business Case. Manual Yes/No Checklist Questions: ROI is consistent with the current Business Case
4 | In addition to meeting the criteria for a rating of 3: The answers to all other questions in the CPIC: Major and Non-Major Investments – Overview and Details tab are answered in detail with information provided in all other sections of the business case. The description covers all parts of the question, which includes the Investment’s purpose, goals, and current or anticipated benefits (quantitative and/or qualitative), as well as the Investment’s specific contribution to mission delivery or Agency management support functions and identify key customers, stakeholders, and other beneficiaries. Manual: Yes/No Checklist question: The answers are in detail and are consistent with information provided in all other sections of the business case. Return on Investment (ROI) explains the qualitative and quantitative benefits of the investment. If an investment does not have a positive ROI, the section includes justification for maintaining the investment. For additional details, refer to slide – Return on Investment (ROI). Manual: Yes/No] Checklist Question: The description covers all parts of the question, which includes the Investment’s purpose, goals, and current or anticipated benefits (quantitative and/or qualitative), as well as the Investment’s specific contribution to mission delivery or Agency management support functions and identify key customers, stakeholders, and other beneficiaries. Mission Area Assistant CIO has added self assessment Rating summary. NOTE: Updates are required for the quarterly and semi-annual submissions. Automated Response: Yes/No. Information is on the CIO rating tab
SUMMARY | This criterion is intended to ensure Investment Owners provide and update the required Investment information in AgMax. AgMax Form/Tab: : CPIC: Major and Non-Major Investments / Overview and Details, Investment Summary, and Investment Funding
Required Documents | Templates can be found on the IITGF Deliverable Matrix page: Investment Charter, Alternatives Analysis (AoA) – Include Cost Benefit Analysis
UPDATE

## Slide 13
Scoring Criteria: Investment Overview (Continued)
Score | 
3 | In addition to meeting a criteria for a rating of 2: All the questions on the CPIC: Major and Non-Major Investments – Overview and Details tab are answered. [Manual: Yes/No] Checklist Question: All the questions on the CPIC: Major and Non-Major Investments – Overview and Details tab are answered. All the narrative questions are complete and consistent with information provided in all other sections of the Business Case. [Manual: Yes/No] Checklist Question: All the narrative questions are complete and consistent with information provided in all other sections of the Business case. Investment level AOA with Cost Benefit Analysis and Charter are completed in FINAL version and required signatures are obtained.[If Final Version is YES and Signature Required is YES] NOTE: If PM has changed, a Charter Addendum with MA CIO signature is required. For additional details, reference to slide – Artifacts Required for All CIO Ratings. Return on Investment (ROI) is not consistent with AoA. Manual: Yes/No Checklist question: ROI is consistent with the current and approved Alternatives Analysis. Mission Area Assistant CIO has not added self assessment rating summary. NOTE: Updates are required for the quarterly and semi-annual submissions. [Automated Response: Yes/No. Information is on the CIO rating tab
2 | In addition to meeting a criteria for a rating of 1: Investment current and/or anticipated benefits have not been updated in over a year. (Updates are required every fiscal year) [Automatic calculation – Last update date on the Overview & Detail tab (current and/or anticipated benefits ) Return on Investment (ROI) does not explain the qualitative and quantitative benefits of the investment. [Manual: Yes/No] Checklist Question: The description covers all parts of the question, which includes the Investment’s purpose, goals, and current or anticipated benefits (quantitative and/or qualitative), as well as the Investment’s specific contribution to mission delivery or Agency management support functions and identify key customers, stakeholders, and other beneficiaries. Integrated Program/Project Team (IPT) Table is not completed. [Automatic calculation – Information completed on the Overview & Detail tab]
1 | Investment charter not provided [If NO/Not Provided] or updated within the updated frequency timeframe [365 date from the signed charter]. CHECK FREQUENCY TIMEFRAME. AoA has not been provided or updated within the updated frequency timeframe. [If NO/Not Provided] or updated within the updated frequency timeframe [365 date from the signed AOA]. If not provided, agency must provide MA Assistant CIO memo indicating why an AoA is not required at the required frequency. No evidence or there is conflicting/inconsistent information.
NOTE: Mission Area Assistant CIO self assessment CIO Rating Comments must be updated on the CIO Rating form
Required Documents/Final Version/Required Signature/Data Updated
Final Version Options = Yes/No/N/A
Remove Date Uploaded in AgMax

## Slide 14
Scoring Criteria: Performance Metrics
SUMMARY | This criterion is intended to ensure O&M Investments have adequate Performance Metrics defined and consistent with FEA Performance Reference Model (PRM)), established metric targets, progress tracked against established targets, and that OA and Post Implementation Reviews (PIR) are performed. NOTE: A project must be mapped to an existing metric ID or New Metric Description. There may be metrics at the investment levels that will not be mapped to a specific projects (i.e. Customer Satisfaction, Operational Efficiencies) AgMax Form/Tab: : CPIC: Major and Non-Major Investments / Operational Data
Required Documents | Templates can be found on the IITGF Deliverable Matrix page: DME: Post Implementation Review DME and MIXED (DME and O&M): Post Implementation Review & Operational Analysis O&M: Operational Analysis / Performance Metrics: Investment Charter NOTE: Investment Charter contains Key Performance Indicators (KPIs), which are a higher level than operational metrics. The Operational Analysis contain detailed metrics that relate to the KPIs.
Score | 
5 | In addition to meeting the requirements for a rating of 4: Performance trend for 90-100% of metrics have been MET consistently throughout the trend assessment period. TREND Assessment – Performance metric has been MET for the following assessment periods: Monthly = 3 reporting periods ¦ Quarterly = 2 reporting periods ¦ Semi-Annual = 2 reporting periods ¦ Annual = 2 reporting periods. 90-100% of performance metrics have been met for the current reporting period (MET?=YES). See Performance Frequencies . A signed Annual Operational Analysis, if required, aligns to the goals and targets provided within the business case and Investment Charter Post Implementation Review , if required, aligns to the goals and targets provided within the business case and Investment Charter Cost Savings/ Avoidance: Total of 4 or more Initiatives reported
4 | In addition to meeting the requirements for a rating of 3: Cost Savings / Avoidance: Total of 1-3 Initiatives reported Performance Criteria for a score of 4 will be implemented at future version
UPDATE

## Slide 15
Scoring Criteria: Performance Metrics (Continued)
Score | 
3 | In addition to meeting the requirements for a rating of 2: Mission Area Assistant CIO has approved all performance metrics. NOTE: Investment Performance Metrics/Success Criteria are contained on the Investment Charter. The investment charter and mapping performance metrics to Agency Strategic Objective/Agency Priority Goal – Codes is an OMB requirement. PMs should review the performance measures with the MA CIO, obtain MA CIO concurrence (email) and upload as supporting evidence. The Performance Metrics table includes the required 5 performance metrics. No Init Reported Performance trend for >=50% of metrics have been MET consistently throughout the trend assessment period. TREND Assessment – Performance metric has been MET for the following assessment periods: Monthly = 3 reporting periods ¦ Quarterly = 2 reporting periods ¦ Semi-Annual = 2 reporting periods ¦ Annual = 2 reporting periods. ≥50% of performance metrics have been met for the current reporting period (MET?=YES). See Performance Metric Frequencies . A signed Operational Analysis is uploaded to AgMax. A signed Post Implementation Review is uploaded to AgMax. Cost Savings / Avoidance: No Initiatives reported; however, Current ROI statement provided on the investment Is the ROI Current (Y/N) Trigger if ROI has not been updated in 365 days
2 | In addition to meeting the requirements for a rating of 1: Cost Savings / Avoidance: No Initiatives Reported and ROI is not current; however, Performance Metrics maps to Agency Strategy Goal (ASO/ Agency Priority Goals (APG) Performance Criteria for a score of 2 will be implemented at future version

## Slide 16
Scoring Criteria: Performance Metrics (Continued)
Score | 
1 | The Performance Metrics table DOES NOT have the required 5 performance metrics. Current and signed Post Implementation Review has not been provided within the updated frequency timeframe (6 months after major release implementation and immediately following termination of system(s) or investment.). Performance trend for <50% of metrics have been MET consistently throughout the trend assessment period. TREND Assessment – Performance metric has been MET for the following assessment periods: Monthly = 3 reporting periods ¦ Quarterly = 2 reporting periods ¦ Semi-Annual = 3 reporting periods ¦ Annual = 2 reporting periods. <50% of performance metrics have been met for the current reporting period (MET?=YES). See Performance Metric Frequencies . Current and signed Operational Analysis has not been provided within the updated frequency timeframe. No evidence or there is conflicting/inconsistent information. Cost Savings / Avoidance: No Initiatives reported, and no performance metrics mapped to ASO/APG, and ROI is not current.
NOTE: The Performance metrics table in the Operational Data tab contains the calculated field (MET?) which is based upon the last entry of the actual metric against the CY Target.
The options for Measurement Condition are Over Target / Under Target. See example of how this is calculated.
Last Actual | CY Target | Measurement Condition | Met? | Reporting Frequency
5 | 10 | Under Target | Yes | Monthly
5 | 10 | Over Target | No | Monthly

## Slide 17
Scoring Criteria: FAC P/PM Certification
SUMMARY | This criterion is intended to ensure that the Investment Managers have the required FAC- P/PM Certification levels which is contained in DR 3130-011 Information Technology Program and Project Manager Certification Requirements. AgMax Form/Tab: : CPIC: Major and Non-Major Investments / Overview and Details (PM Table) For information on Certification status, reach out to your Agency PM/PgM Certification representative. A list of contacts is available on the CPITGD SharePoint site. NOTE: To maintain a FAC-P/PM, certified professionals are required to earn 80 CLPs of skills currency every two years. The two-year anniversary is set by the date the individual is certified. If an individual does not meet the 80-hour CLP requirement, his or her certification will lapse. In order to reinstate the certification, at a minimum, he or she must complete 80 hours of continuous learning within a two-year period. For more information, go to: https://www.fai.gov/certification/program-and-project-managers-fac-ppm.
Required Documents | FAC-P/PM Certification or FAC-P/PM Extension
Score | 
5 | In addition to meeting the requirements for a rating of 3: The Investment Manager Information Table in the CPIC: Major and Non-Major Investments – Overview and Details tab is complete AND the IT Investment Manager is: FAC-P/PM Level 3 certified if it is a USDA Major or FAC-P/PM Level 2 certified if it is a USDA Non-Major The appropriate FAC-P/PM certification documentation is current, or recertification is uploaded in AgMax.
3 | In addition to meeting the requirements for a rating of 1: The Investment Manager Information Table in the CPIC: Major and Non-Major Investments – Overview and Details tab is complete. FAC-P/PM certified: NOT at the required level for this investment and Date assigned as Investment Manager is less than 1 year of FAC-P/PM certification date. (i.e. Investment Manager is assigned to Major Investment in 01/2019 and has FAC-P/PM Level 2 and 1 year from assignment HAS NOT passed) Current FAC-PPM Certification and FA- P/PM Extension and other supporting documentation showing Investment Manager is working on certification are uploaded to AgMax. NOTE: Investment Managers should have the proper certification within 12-months of being assigned to an Investment. Recertification Date has not expired.
UPDATE

## Slide 18
Scoring Criteria: FAC P/PM Certification (Continued)
Score | 
1 | Investment Manager Information Table is not complete. FAC-P/PM certification has expired. Recertification date has passed. Investment Manager has indicated NO Certification AND timespan is greater than 1 year of Date assigned to the Investment. (i.e., PM is assigned to Major Investment in 01/2019 and has FAC-P/PM Level 2 and 1 year from assigned date HAS passed).

## Slide 19
SUMMARY | This criterion is intended to ensure Investment contracts are competitive and address acquisition risk mitigation to Federal Government. AgMax Form/Tab: CPIC: Major and Non-Major Investments / Contracts
Required Documents | Templates can be found on the IITGF Deliverable Matrix page: Acquisition Management Plan (AMP) Inter-Agency Agreements (IAAs) Contracting Officer or Contracting Officer Representative’s FPDS.gov confirmation email AAR Summary Scorecard
Score | 
5 | In addition to meeting the criteria for a rating of 4: Acquisition documentation provides details on how the acquisitions will be planned, executed, and managed throughout the life of the investment or project. All contracts, tasks orders, Memoranda of Understanding (MOU) including the contract type, as specified in the FAR – Part 16, and the reason for the contract type selection are included in the Acquisition Management Plan document. List of IAAs (Name, IAA Partners, Period of Performance, Total Cost) has been uploaded in AgMax. All known planned contracts, task orders, and Memoranda of Understanding (MOU) are included on the Acquisition Strategy - Planned Procurements table.
4 | In addition to meeting the criteria for a rating of 3: AAR Summary Scorecard overall score is Green (3). AAR numbers identified on the Contract table. NOTE: AAR Number is not required on contract values less than $25K. Evidence of contracts from FPDS.Gov (i.e. snapshot) aligns with information on contract table and has been uploaded in to AgMax. Evidence can also be Contract Officer (CO) or Contracting Officer Representative (COR) email confirmation indicating contracts are/will be included in FPDS.gov. Supporting evidence are to be updated upon any contract changes and on a yearly basis.
3 | In addition to meeting the criteria of a rating of 2: Required AMP is current with required signature. Planned acquisitions indicates “Yes” but no planned acquisitions have been identified. If no planned acquisitions have been identified, a business justification will need to be provided. The Existing Contracts table has at least 1 active contract. AAR Summary Scorecard overall score is Yellow (2).
Scoring Criteria: Contracts
UPDATE

## Slide 20
Scoring Criteria: Contracts (Continued)
Score | 
2 | In addition to meeting a criteria of 1: AMP does not address acquisition risk mitigation to Federal Government. AAR numbers are not identified in the existing contract table (Applicable contracts containing FY20 AARs and beyond). AAR Summary Scorecard overall score is Red (1).
1 | No evidence or there is conflicting/inconsistent information. Contract table not completed. No evidence of FPDS.gov confirmation provided or uploaded to AgMax. Current and signed AMP has not been provided within the updated frequency timeframe.

## Slide 21
Scoring Criteria: Risk Management
SUMMARY | This criterion is intended to ensure Investments develop a Risk Management Plan and manage an Investment Risk Register) throughout the life cycle. Investment Risk Registers should provide management with transparency on the probability and impact of the active risks, as well as the adequacy of the risk mitigation strategy for each risk. NOTE: AgMax should contain the last 3 months of risk logs and each should contain Risk Description/Mitigation Strategy/Contingency Plan AgMax Form/Tab: CPIC: Major and Non-Major Investments / Investment Risks
Required Documents | Templates can be found on the IITGF Deliverable Matrix page: Risk Management Plan / Risk Register
Score | Applies to All Investment Life Cycle Types
5 | In addition to meeting the requirements of a rating of 4: Risk Mitigation Strategies are in place for all identified active risks, and includes triggers, and handling options, for example, assume/accept, Avoid, Control, Transfer, or Watch/Monitor. Risk management practices exhibit evidence of active monthly updates and controls and includes mitigation follow up actions which are documented in the Risk Register.
4 | In addition to meeting the requirements of a rating of 3: Each identified Risk Area with a risk has a short description, mitigation strategy and a contingency plan. Risk Register contains a cross-section of applicable risk areas: Technology, Project Schedule and Resources, Business, Organizational and Change Management, Strategic, Security, Privacy, Data, Integration, Project Team, Requirements, Cost, and Project Management. All risk areas should be reviewed and identified if applicable. Individual risks with the highest combined probability and impact score in each applicable Risk Area have been used to rate the Risk Area in the business case (exception…if more than one individual risk within a Risk Area has the same combined score, the individual risk with the highest impact score has been used to rate the Risk Area). Actionable Risk Mitigation Strategies and Contingency Plans have been identified for all individual risks in the Risk Register.
3 | In addition to meeting the requirements for a rating of 2: The Risk Register is current, complete, and uploaded to the supporting documents tab in AgMax. NOTE: Risks Areas must be identified in the Risk Register. Active? field has been answered for each of the 13 Risk Areas. If Active field is YES, it must be recorded in the risk register. A current Risk Management Plan includes required signatures. NOTE: Agency approach of how it will handle risks with a combined probability and impact score of a ‘6’ or greater must be included in the Risk Management Plan.
2 | Risk Management Plan does not contain required signatures, is incomplete or outdated and doesn’t align with the current scope of the investment. Risk Register incomplete or outdated. NOTE: Must be updated every 45 Days. Unchanged ‘Red’ risk rating(s) for the 90 days and have not been mitigated or resolved sufficiently to justify an improved rating. For further details, see slide – Risk Management Exposure Chart.
1 | No evidence or there is conflicting/inconsistent information.
UPDATE

## Slide 22
Scoring Criteria: Project Management
SUMMARY | ***IMPORTANT: OVERALL CIO RATING WILL NOT BE GREATER THAN THE SCORE FOR THIS SECTION. *** Investment performance is a key management criterion, as it affects the overall health of the investment and is publicly accessible. This criterion is intended to measure DME and O&M project performance and ensure minimal re-baselining due to investment/project management issues. Referenced cost and schedule variance thresholds align to the Federal IT Dashboard. AgMax Form/Tab: CPIC: Major and Non-Major Investments / Projects and Activities
Required Documents | Templates can be found on the IITGF Deliverable Matrix page: Project Charter / No templates for the following: Integrated Master Schedule / Iterative development: Product Backlog Sprint Backlog Burndown Chart
Score | 
5 | In addition to meeting the requirements for a rating of 4: All projects require Mode of End User engagement to be entered into AgMax with one of the following modes: User Acceptance Testing Through Planning & Needs Development Other (With explanation Provided) Results from Mode of End User Engagement must be entered into AgMax for all projects. The date and results of the activity’s last end user engagement activity is entered into AgMax for all projects. Last three dates of release to production identified in the AgMax Project Activity Table for software development projects. Last three dates of release to test identified in the AgMax Project Activities Table for software development projects. The estimated time between code creation and release identified in the AgMax Project Activities Table for software development projects. % of Investment projects perform incremental development is > 41% -100%.*
4 | In addition to meeting the requirements for a rating of 3: A complete Project Charter is uploaded into AgMax. Integrated Master schedule is uploaded and reflects overall investment schedule. For investments managing their work using agile methodologies, User stories or Backlog for iterative development have been uploaded. All active project do not have a cost or schedule variance greater than +/- 10%. There are no project re-baselines in a fiscal year due to scheduling or budget variances caused by investment/project management issues. % of Investment projects perform incremental development is > 25% - 40%.*
3 | In addition to meeting the requirements for a rating of 2: If there is a project replan or rebaseline a memo from Mission Area Assistant CIO is required for major investments. For non-major investments memo required from IT Director or CIO designee. There is no more than 2 project re-baseline in the current fiscal year due to scheduling or budget variances caused by investment/project management issues. O&M PROJECTS equal to or greater than $200K : If current O&M projects are funded for $200,000 or more annually, on O&M project and related project activities are to be reported in the same way as DME projects (Project (C.1) and Project Activity (C.2)) Tables.
UPDATE

## Slide 23
Scoring Criteria: Project Management (Continued)
Score | 
3 | In addition to meeting the requirements for a rating of 2: Significant variances ± 10% are explained in Corrective Action Plans (CAPs) and/or rebaseline requests are in place as appropriate. Project Table: Date spans do not exceed three (3) years or broken out in the measurable phases (i.e. SDLC cycle). Project releases do not exceed six (6) months for software development projects. Project start/completion dates or lifecycle cost have not changed since last quarterly review. All required dates are entered in Project table. Project cost and schedule variances and scope changes are identified All active projects has a cost or schedule variance of +/- 10-30%. Project Activities: Project activities table contain at least two (2) activities for each associated project. All projected/planned/actual start or completion dates/costs have been entered as applicable. % of Investment projects perform incremental development is > 11% - 24%.*
2 | In addition to meeting the requirements for a rating of 1: Projects that responded “Yes” to “Primarily a Software Development or Deployment Project?” in Projects Table [MM-DD-YYYY or N/A] must have planned testing and production release dates identified in the project activities table. A project does not contain an existing metric ID or new metric description. % of Investment projects perform incremental development is > 6% - 10%.*
1 | Any active projects have a cost and/or schedule variance of ≥+- 30%. No current active projects included in the Projects Table. Applicable project scheduling documentation has not been provided. Any active project has not identified the project type. % of Investment projects perform incremental development is > 0% -5%.*
* = Incremental Development can be identified for projects that release a usable functionality within six months. Per OMB, anything longer is not considered an Incremental Development project.

## Slide 24
Scoring Criteria: IT Governance
SUMMARY | The intent is to demonstrate that standardized governance processes and procedures are in place at both the Department and Agency level, and are designed to improve IT management; maximize return on IT investment; provide a more effective IT solution with a close alignment with the business and mission needs and objectives; are consistent with USDA IT Strategy and Policy; and provides accountability and transparency in the decision-making process that has an enterprise impact on IT within the USDA. This criterion applies to USDA Major, Standards and Non-Major IT Investments. AgMax Form/Tab: CPIC: Major and Non-Major Investments / IT Governance
Required Documents | Agency or Staff Office (Mission Area CIOs) Investment Review Board (IRB) Charter (or other executive level-chartered governance body). Signed by Chair of Governance Board. Agency or Staff Office (Mission Area CIOs) CIO Certification Statement within the Investment Charter, Memo or Email uploaded to AgMAX for this investment that affirms that active software development project(s) are implementing incremental (iterative/agile) development methodologies. Signed by Mission Area ACIO. Governance Board Decision Material evidenced by submission of the board's meeting minutes or decision memo in AgMAX. Does not need to be signed. CPITGD analyst to use their judgement on elated materials submitted. For additional information, please contact: AgITGovernance@ocio.usda.gov
Score | 
5 | In addition to meeting the requirements of a rating of 4: Program Review or TechStat has not been required within the last year. If the investment has been briefed to the E-Board (or USDA CIO in lieu of the E-Board) and all corrective actions addressed and closed on or prior to the suspense date. NOTE: The E-Board generally meets for Major Investments; however, OCIO can determine what investments will be reviewed. Investments and any key projects have been briefed, at a minimum of a quarterly basis to the applicable Governance Boards (to include the Integrated Advisory Board (IAB) and E-Board) and official outcome documentation is uploaded to the Department’s Portfolio Management tool within 3 days of the completion of the investment briefing.
4 | In addition to meeting the requirements of a rating of 3: All corrective actions have been addressed and closed, on or prior to the suspense date. If applicable, a TechStat or Program Review has been held and action items / conditions have been closed on or prior to the suspense date. No action items/ conditions/ corrective actions have been identified from the Governance Board Decision Materials. Investments and any key projects have been briefed, at a minimum of a bi-annual basis to the applicable Governance Boards (to include the Integrated Advisory Board (IAB) and E-Board) and official outcome documentation is uploaded to the Department’s Portfolio Management tool within 3 days of the completion of the investment briefing.
UPDATE

## Slide 25
Scoring Criteria: IT Governance (Continued)
Score | 
3 | In addition to meeting the requirements of a rating of 2: For any investment that contains an active incremental development project, there is a corresponding Mission Area Assistant CIO certification statement added to the Investment Charter. The investment does not require an Integrated Baseline Review (IBR) or Rebaseline at time of scoring. For more information on IBR and rebaseline requirements, please refer to your capital planning liaison. This investment currently does not meet the requirements for a program review or TechStat (i.e., 2 consecutive ratings of yellow or red). If applicable, TechStat or Program Review has been held and action items / conditions are being addressed. The Agency or Staff Office (Mission Area) governance IRB Charter is finalized with the required signatures and uploaded in AgMAX. Investments and any key projects have been briefed, at a minimum of an annual basis to the applicable Governance Boards (to include the Integrated Advisory Board (IAB) and E-Board) and official outcome documentation is uploaded to the Department’s Portfolio Management tool within 3 days of the completion of the investment briefing.
2 | In addition to meeting the requirements of a rating of 1: Single project requires Rebaseline within the current fiscal year and has not met with governance board. More than two investment Rebaselines have been required within the current fiscal year. Two or more projects require Rebaselines approvals from a governance board. The investment currently meets the requirements for a Program Review or TechStat (i.e., 2 consecutive ratings of yellow or red) and the meeting has not been held (2 Consecutive Reds - THIRD REVIEW). Investments and any key projects have not been briefed in over 12 months to the applicable Governance Boards (to include the Integrated Advisory Board (IAB) and E-Board) and official outcome documentation is uploaded to the Department’s Portfolio Management tool within 3 days of the completion of the investment briefing.
1 | The Agency or Staff Office (Mission Area) governance IRB charter is unavailable, incomplete, draft, or unsigned. Agency or Staff Office (Mission Area CIOs) CIO Certification Statement is unavailable, incomplete, draft, or unsigned. Governance Board Decision Material is unavailable, incomplete, draft, or unsigned. Investments and any key projects have not been briefed to the applicable Governance Boards (to include the Integrated Advisory Boards (IAB) and E-Board) and official outcome documentation is uploaded to the Department’s Portfolio Management tool within 3 days of the completion of the investment briefing.

## Slide 26
Scoring Criteria: Technology Business Management
SUMMARY | This criterion is intended to support the ongoing implementation of the Technology Business Management (TBM) framework across USDA. For more information about USDA’s ongoing TBM implementation, reach out to AgTBMWorkingGroup@ocio.usda.gov. Scoring for this criterion is fully automated (with the option for manual override) and based on the following three standard metrics with varying targets to support a score of 1, 3, or 5: The first metric aligns with the federal-wide OMB and PMA requirement to categorize 100% of planned IT spend/budget according to the standard TBM Cost Pools and IT Towers (TBM Taxonomy 3.0). The second metric assesses the percentage of an investments total DLCC that are associated with an IT Asset (i.e., System, Application, Application Component, or Platform). IT Investment DLCCs are comprised of Asset (formerly “System”) and Non-Asset (Formerly “Non-System”) costs. In most scenarios, most of an investment’s costs should be tied to IT Assets. As exceptions to this are identified, the manual scoring override will be used. IT Assets do not apply to Standard IT Management Investments The third metric assess the percentage of an investment’s IT Asset (formerly “System”) DLCC costs that are mapped to the TBM Service Hierarchy. Agencies/Staff Offices are expected to map their Asset costs to the TBM Service Hierarchy on the Capability Associations tab of the IT Asset Detail Form in AgMAX. AgMax Form(s)/Tab(s): Detailed Life Cycle Costs (DLCC) / Non-Asset Costs and Asset Costs; Asset/Non-Asset DLCC and Capability Associations Reference: TBM Taxonomy 3.0
Score | 
5 | In addition to meeting the requirements for a rating of 3: IT Towers and DLCC/Cost Pool variance is <1% for PY, CY, and BY. % IT Asset DLCC costs ≥ 75%. % of IT Asset DLCC Costs categorized by TBM Services Hierarchy ≥75%.
3 | In addition to meeting the requirements for a rating of 1: IT Towers and DLCC/Cost Pool total variance is <5% for PY, CY, and BY. % of IT Asset DLCC costs ≥ 50%. % of IT Asset DLCC Costs categorized by TBM Services Hierarchy is ≥25%.
UPDATE

## Slide 27
Scoring Criteria: Technology Business Management (Continued)
Score | 
1 | IT Towers and DLCC/Cost Pools total variance is >5% for PY, CY, and BY. % IT Asset DLCC Costs < 50%. % of IT Asset DLCC Costs categorized by TBM Services Hierarchy <25%.

## Slide 28
In the PROCESS PANE – search:
MONTHLY REVIEW CHECKLIST
FORM: Investment – Monthly Review Checklist
Monthly Review Checklist
TABS: Each tab has automated complaint/non-compliant messages based upon business case data and/or CPITGD assessment responses
Tab
Tab

## Slide 29
Please send any questions or comments to Capitalplanningdivision@usda.gov and/or contact your CPITGD Liaison.
Questions?

## Slide 30
Appendices

## Slide 31
Artifacts Required for All CIO Ratings (1 of 5)
# | Artifact | High-Level Description | Impacted Criterion | Update Frequency
1 | Alternative Analysis (AA) | All business problems may be addressed by any number of alternative projects. While the business case is the result of having selected one such option, a brief summary of considered alternatives should also be included — one of which should be the status quo, or doing nothing. The reasons for not selecting the alternatives should also be included. Signature(s) Required: MA CIO, CFO or Budget Officer | Investment Overview | ~3 Every Years (recommend re-assessing selected alternative to determine if technology/ services should be consolidated, eliminated, moved to cloud, etc.)
2 | Investment Charter | Authorizes a new investment and execution of all projects known at the time as well as the operation and maintenance of the systems delivered by them. If the scope of the investment is expanded to include one or more additional projects, an addendum should be attached to the original investment charter for each new authorized project. Signature(s) Required: MA CIO, PM, Business Sponsor | Investment Overview | Update as needed to ensure scope, risk, schedule, and cost are current
3 | Acquisition Management Plan | Documents and informs investment or project stakeholders about how the acquisitions will be planned, executed, and managed throughout the life of the investment or project. The document includes the approach to be taken for items such as the actual acquisition, contracting, and fiscal, legal, personnel, considerations, etc. As a part of the acquisition strategy, it should also address any policy, process, regulatory, etc. necessary to comply with FAR, and any other federal and USDA requirements related to the specific acquisition. The plan also should include background information such as cost, capability or performance, delivery or performance period requirements, trade-offs, risks and any acquisition streamlining efforts (e.g., draft solicitation, pre-solicitation conferences to stimulate industry involvement). Signature(s) Required: MA CIO, PM, and CFO or Budget Officer | Contract/ Acquisition Strategy | Yearly (and more frequently, as needed)
Templates can be found on the IITGF Deliverable Matrix page:
NOTE: The term Investment Manager is often used in conjunction with PM; therefore, for the purposes of this scoring criteria, PM can also refer to IM
UPDATE

## Slide 32
Artifacts Required for All CIO Ratings (2 of 5)
# | Artifact | High-Level Description | Impacted Criterion | Update Frequency
4 | Risk Management Plan (RMP) | Defines how risks associated with a specific project or a business process will be identified, analyzed, and managed. It outlines how risk management activities will be performed, recorded, and monitored throughout the lifecycle of the project and provides templates and practices for recording and prioritizing risks by the Risk Manager and/or Risk Management Team. Signature(s) Required: MA CIO, PM | Risk Management Overview | As needed, minimum yearly
5 | Risk Register | Logs risks and tracks them throughout its lifecycle, and includes information such as Current Status, Risk Impact, Probability of Occurrence, Risk Map, Risk Description, Project Impact, Risk Area, Symptoms, Trigger, Risk Response Strategy, Response Strategy, Contingency Plan. The Risk register is project based; therefore, USDA requires reporting risk at project level. The most significant risks (high impact/high possibility) that affect the investment should be included in the Investment Risk table. Should be updated every 45 days. Signature(s) Required: None. PM is responsible for content submitted. | Risk Management Overview | Every 45 Days
6 | Integrated Master Schedule (IMS) | Project schedule to track execution that help the effectiveness of the established plans and processes in the development of the IT investment. There is no template; as the program manager can use their tool of choice. Signature(s) Required: None. PM is responsible for content submitted. | Project Management | Monthly
7 | Project Charter | Documents the formal authorization of the project. Also includes information on project scope, project manager, summary of milestone schedule, and project budget and funding source. Project Charter should identify all projects in the IT Business Case Detail – Projects Table (formerly known as B1 Table). A Project Charter can be submitted separately for each project or as a single document with all projects included. Signature(s) Required: PM, Project Manager | Project Management | As Needed
UPDATE
Templates can be found on the IITGF Deliverable Matrix page:
NOTE: The term Investment Manager is often used in conjunction with PM; therefore, for the purposes of this scoring criteria, PM can also refer to IM

## Slide 33
Artifacts Required for All CIO Ratings (3 of 5)
# | Artifact | High-Level Description | Impacted Criterion | Update Frequency
8 | Post Implementation Review (PIR) | Helps determine whether investments have achieved expected benefits, such as lowered cost, reduced cycle time, increased quality, or increased speed of service delivery. PIR provides an assessment of the implemented investment, including an evaluation of the development process, and also indicates the extent to which the USDA’s decision-making processes are sustaining or improving the success rate of IT investments, and assess lessons learned. Signature(s) Required: Business Sponsor, PM | Performance Metrics | 6 months after major release implementation and immediately following termination of system(s) or investment
9 | Operational Analysis (OA) | There are annual OA template, checklist, overview, and operational review template. Annual OA template includes information such as investment overview, strategic and business results, user/customer assessment, performance assessment, financial performance, innovation, enterprise architecture, security and privacy, and recommendations. OA template also includes investment manager’s recommendation on whether the investment should remain in steady state, commence planning for DME (Development, Modernization, & Enhancement) in order to ensure continued investment viability, discussed at IT-Investment Review Board, or IT-Investment Review Board does not need to discuss this investment. Signature(s) Required: MA CIO, Business Sponsor, PM | Performance Metrics | Annual
10 | FAC PPM Certification | Demonstrates that Investment Owner/Project Manager is FAC PPM certified. FAC PPM provides a structured approach for IT P/PMs to develop accurate requirements, define measurable performance metrics, and manage acquisition activities to ensure that intended business and technical outcomes are achieved for major and non-major IT investments. Signature(s) Required: None | FAC P/PM Certification | Change in PM (requires updated certification in AgMAX)
11 | Agency IRB Charter | Investment Review Board Charter is to authorize the Agency-level governance body. Signature(s) Required: MA CIO | IT Governance | Update as specified in the Charter itself
12 | CO/COR FPDS.gov email | Contracting Officer or Contracting Officer Representative are to send FPDS.gov email confirmation of contracts identified on the contracts table. A picture of the contract data in FPDS.gov is acceptable if sent from CO/COR. Signature(s) Required: None. PM is responsible for content submitted. | Contract/ Acquisition Strategy | Annually and as updates are made to contracts table
Templates can be found on the IITGF Deliverable Matrix page:
NOTE: The term Investment Manager is often used in conjunction with PM; therefore, for the purposes of this scoring criteria, PM can also refer to IM
UPDATE

## Slide 34
Artifacts Required for All CIO Ratings (4 of 5)
# | Artifact | High-Level Description | Impacted Criterion | Update Frequency
13 | IRB Meeting Minutes of Decision Memo | Agencies are responsible for managing their Information Technology (IT) resources to improve the delivery to services to the public, to assist program management at both Departmental and agency levels, to provide cost-effective technologies and solutions to satisfy program requirements, and to promote sharing of these resources to the greatest extent possible. To assure that information management activities reflect the goals and priorities of the Department and agency programs, each Mission area (MA) or Agencies will establish an Investment Review Board (IRB), that will provide policy direction for IT resource activities as well as review and approval of specific IT resources actions. The decision memo or meeting will serve as evidence that the MAs or Agencies in accordance with USDA policy or guidance. Signature(s) Required: MA CIO or Governance Board Chair (Memo), NOTE: No signatures required for meeting minutes and presentation /briefing | IT Governance | Annually or as the investment is reviewed by IRB
14 | Mission Area Assistant CIO Certification of Incremental Development | Ensures that the CIO of the USDA reports all major IT investment information related to incremental development accurately in accordance with OMB. The USDA CIO has delegated authority to each MA CIO to certify the incremental development of IT Investments and its projects on behalf of the USDA CIO. The MA CIO certification can be provided as part of the Investment Charter or separate email. Signature(s) Required: MA CIO | IT Governance | Annually or as new projects are created / added to the investment
15 | Product Backlog | The Product Backlog is an ordered list of everything that is known to be needed in the product. It is the single source of requirements for any changes to be made to the product. The Product Backlog lists all features, functions, requirements, enhancements, and fixes that constitute the changes to be made to the product in future releases. Signature(s) Required: None | Project Management | As Needed
16 | Sprint Backlog | The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a "Done" Increment. Signature(s) Required: None | Project Management | As Needed
Templates can be found on the IITGF Deliverable Matrix page:
NOTE: The term Investment Manager is often used in conjunction with PM; therefore, for the purposes of this scoring criteria, PM can also refer to IM
UPDATE

## Slide 35
Artifacts Required for All CIO Ratings (5 of 5)
# | Artifact | High-Level Description | Impacted Criterion | Update Frequency
17 | Burn Down Chart | A large graph relating the quantity of work remaining (on the vertical axis) and the time elapsed since the start of the project (on the horizontal, showing future as well as past). Signature(s) Required: None | Project Management | As Needed
18 | Cost-Benefit Analysis | Cost-Benefit analysis refers to the recommended technique to use in a formal economic analysis of government programs or projects.. Where benefits and costs can be quantified and expressed in monetary units, cost-benefit analysis provides decision makers with a clear indication of the most efficient alternative, that is, the alternative that generates the largest net benefits. Signature(s) Required: None NOTE: This document can be part of the Alternatives Analysis or a standalone document. | Investment Overview | In tandem with the Alternatives Analysis
19 | Joint Certification Memo | A joint statement from the Mission Area/ Staff Office ACIO, CFO, Agency Budget Officer, Privacy Officer, and MA OBPA Representative certifying the availability of approved Current Year (CY) and proposed Budget Year (BY) funding for the Agency’s IT Portfolio Investments as reported in AgMAX and as provided in the OBPA Fiscal Year (FY) Estimate Data Call. Signature(s) Required: MA ACIO, CFO or Budget Officer, Privacy Officer, and MA OBPA Representative. | IT Governance | 2x Annually (Annual Submission and Pass back) and as significant changes occur
20 | Inter-Agency Agreements (IAA) | A written agreement between two Federal agencies, or major organizational units within an agency, which specifies the goods to be furnished or tasks to be accomplished by one agency (the servicing agency) in support of the other (the requesting agency). Signature(s) Required: None | Contract/ Acquisition Strategy | As Needed
UPDATE
Templates can be found on the IITGF Deliverable Matrix page:
NOTE: The term Investment Manager is often used in conjunction with PM; therefore, for the purposes of this scoring criteria, PM can also refer to IM

## Slide 36
USDA OCIO Performance Requirement 1: IT Spend
Increase cost saving/avoidance metrics and incremental development project reporting by 25% in support of improving USDA Portfolio Savings and CIO Authorities ratings on the FITARA Congressional Scorecard. (Level 3)
Increase cost saving/avoidance metrics and/or incremental project reporting by 40% in support of improving USDA Portfolio Savings and CIO Authorities ratings on the FITARA Congressional Scorecard. (Level 5)
CIO Scoring Criteria Categories Used – Project Management and TBM (See pages 22–23 & 26–27)
SOURCE: Capital Planning & IT Governance; (IRMC/CPITGD has 3 FITARA Congressional Scorecard Categories – Portfolio Reviews and CIO Authority)
Achieve a score of greater than 75% on the Enterprise Architecture Visioning Environment (EAVE) dashboard for IT assets and critical data reporting. (Level 3) Achieve a score of greater than 90% on the Enterprise Architecture Visioning Environment (EAVE) dashboard for IT assets and critical data reporting. (Level 5)
SOURCE: Enterprise Architecture
Assistant CIOs Performance Assessment
NEW

## Slide 37
USDA OCIO Performance Requirement 2: Supports Implementation and Compliance with FITARA
Improve the IT Management Maturity (ITMM) model level to between a 2.2 and 2.4 (Level 3). Improve the IT Management Maturity (ITMM) model level to between a 2.8 and 3.0 (Level 5)
SOURCE: FITARA
Staff Development: Reskill 5% of Mission Area authorized IT workforce (2210s) in accordance the USDA IT Workforce Plan FY20-FY22 (Level 3). Reskill 15% of Mission Area authorized IT workforce (2210s) in accordance the USDA IT Workforce Plan FY20-FY22 (Level 5).
SOURCE: IT Workforce
Assistant CIOs Performance Assessment - Continued
Performance Requirement | FY2021Q1 | FY2021Q2 | FY2021Q3 | FY2021Q4
USDA OCIO Performance Requirement 1: IT Spend |  |  |  | 
Increase cost saving/avoidance metrics and/or incremental project reporting |  |  |  | 
Enterprise Architecture Visioning Environment |  |  |  | 
USDA OCIO Performance Requirement 2: Supports implementation and compliance with FITARA |  |  |  | 
IT Management Maturity (ITMM) model |  |  |  | 
Staff development |  |  |  | 
NEW

## Slide 38
Major Investment Designation
Investments that meet the below criterial will be designated as a Major Investments:
  Meets Dollar Threshold
    Agency or Staff Office is planning to spend $1 million or more in DME in current-year funding AND
    Total life cycle DME investment costs are equal to or greater than $20M
  Meets Major Investment Definition - DR 3130-008
    The investment has been identified by the USDA Chief Information Officer (CIO) as critical. This may include investments that have one or more of the following attributes:
      Mandated by legislation or Executive Order;
      Require a common infrastructure investment;
      Considered strategic or mandatory-use investments;
      Differ from or greatly impact the Department’s infrastructure, enterprise architecture or standards guidance; and
      Involve multiple-Agency funding.
  USDA Critical Investments
    Such as:
      National Security Investments
      All OCIO Standard Investments (Enterprise Shared Services)

## Slide 39
The information included on the AAR Scorecard is captured from data in AgMax and contains the following for the current fiscal year:
Overall AAR Score for the Investment – Each criterion (1-4) is assigned an equal weight to determine Agency average.
  Failed AAR Administrative Review – Number of times either the Emergency AAR Admin Review or AAR Admin Review outcome is “Disapproved” in Current FY.
  AARs Avg number of times AARs are in Awaiting Agency Feedback Status – Counts the number of AARs where at least one SME set the status to "Awaiting Agency Feedback”
  Emergency AAR Conditional Approval & Resubmittal Elapsed Time – Calculates the number of days between when an Emergency AAR is conditionally approved and resubmitted.
  Percentage of Investments with AARs Submitted (Current FY) – If an investment has at least one PY AAR Funding Item with an overall status of approved.
AAR Scorecard Summary

## Slide 40
Project Cost Variance Calculations
Note: Actual data are used to calculate variance, when available. If actuals data are not available, projected costs are used.
Always use the “Actual” value if both “Projection” and “Actual” are provided for the same activity. Roll-ups are obtained by summing the costs of all the included lowest level child activities.
  For Individual Future Activities or Roll-Ups that contain only future activities:
  Project Cost Variance = 0%
  For Completed or In-Progress Activities and Roll-Ups (which may include some future activities):
  Project Cost Variance = Sum of all “Planned Total Costs” on the table – Sum of all “Projected OR Actual Total Cost” on the table % Project Cost Variance = “Project Cost Variance” / Sum of all “Planned Total Cost” * 100
# | *Project Name | Valid? | Project ID | Objectives / Expected Outcomes | Project Start Date | Project Completion Date | Project Lifecycle Cost | SDLC Methodology | Production Release - 6 Months | Production Release Comment | Date Revised Product deployed in Production | Cost Variance (%) | Cost Variance ($) | Schedule Variance (# of days) | Schedule Variance (%)
Project Cost and Schedule Variance Calculations
Project Cost Variance Calculations:
*Note: Actual data are used to calculate variance, when available. If actuals data are not available, projected dates are used.
Project Schedule Variance Calculations:
Project Schedule Variance in days for an Activity | 
Project Schedule Variance (DEFAULT) | Project Completion Date minus the latest Project Activity Actual Completion Date* from the table (whichever is greatest) Always use the “Actual” value if both a “Projected” and an “Actual” date are provided for the same activity
*Conditional Option | If the C.2 project activity actual completion date is MISSING, calculate project completion date minus latest project activity projected completion date from the table (whichever is greatest); HOWEVER, If the latest project activity actual completion date is MISSING AND the latest project activity projected completion date is GREATER THAN TODAY’S DATE, CALCULATE: Project Completion Date minus today’s date
40

## Slide 41
All risks identified are assessed to identify the range of possible project outcomes. Risks are prioritized by their level of importance and assessed in term of scope, such as risks being realized may impact cost or the schedule may impact a project’s abilities to complete its planned scope within the cost and schedule parameters stated in its governing documents (i.e. Project or IPT Charter).
Per OMB Guidance, risk assessments should include both project and operational risk information from all stakeholders and should be performed throughout the life cycle of the Investment.
Risk Assessment information related to each of the 13 Risk Areas is provided at the Investment level. Risk Area data should be consistent with what is included in management briefings or Agency status reviews on an ongoing basis. If the Investment is managing multiple individual risks within a single Risk Area, provide responses for the overall area based on the individual risk with the highest probability and impact combined score. If multiple individual risks within a single Risk Area have the same combined score, report based on the risk with the higher impact rating. The probability and impact combined score will be the product of the probability and impact estimates using the numerical designations for each probability and impact benchmark provided in Risk Table.
Risk Management – Risk Assessment
Unchanged ‘Red’ risk rating(s) for the past 2 reporting periods (2 quarters) will negative affect the Investment Risk Management rating. The Investment team is recommended to provide a risk response plan for discussion with their USDA Capital Planning and IT Governance Division Liaison.
Rating | Probability |  | Rating | Impact
1 | Very Low – 0-10%, |  | 1 | Very Low – little or no impact on achieving Investment objectives
2 | Low – 11-30%, |  | 2 | Low – some impact on achieving Investment outcome objectives, but has little or no impact on achieving the Agency’s mission
3 | Medium – 31-60%, |  | 3 | Medium – significant impact on achieving Investment outcome objectives, with moderate impact on the Agency’s ability to deliver core mission functions
4 | High – 61-90%, |  | 4 | High – significant impact on both achieving Investment outcome objectives and the Agency’s ability to deliver core mission values but has little or no impact on the Government as a whole
5 | Very High – 91-100%. |  | 5 | Very High – severe impact on executing the Agency’s core mission with ramifications for the Government as a whole

## Slide 42
Risk Management – Risk Exposure Chart
Based on the selection of numerical designations for both Probability & Impact by the Investment Manager, find below how the risk rating is calculated for any given risk. For example, a Risk with probability rated as “Low” (2) and impact rated as “High” (4) will have a combined risk score of 2 x 4 = 8. With a risk score of 8, this risk will receive a Moderate Risk Rating. Use the risk exposure chart below to calculate the risk rating for your investment.
NEW

## Slide 43
Performance Metric Frequencies
As mentioned in the Performance Metrics category, USDA has four frequencies when metrics are to be reported:
  Monthly
  Quarterly
  Semi-Annual
  Annual
See to the right when metrics are required over the Fiscal Year. If followed, your investment will meet Performance Metric trend requirements.
For new metrics, you are given the reporting periods (months) below before being penalized.
  Monthly = 3 (3)
  Quarterly = 2 (8)
  Semi-Annual = 2 (12)
  Annual = 2 (24)
NEW
October
Monthly
November
Monthly
December
Monthly
Quarterly
January
Monthly
February
Monthly
March
Monthly
Quarterly
Semi-Annual
April
Monthly
May
Monthly
June
Monthly
Quarterly
July
Monthly
August
Monthly
September
Monthly
Quarterly
Semi-Annual
Annual Metrics can be submitted at any point during the Fiscal Year
Q1
Q2
Q3
Q4
Performance Metric Frequencies by Month

## Slide 44
Executive Information Technology Investment Review Board (E-Board)
Capital Planning
Advisory Council
Enterprise Security
Governance Council
Critical Partners
Advisory Group
(OHRM ,OCP, DISC, CEC, OBPA,
ENS, CIOC, others as needed)
Integrated Advisory Board (IAB)
Departmental & Enterprise
Advisory / Recommends
Mission Area Investment Review Boards (IRB)
*Agency Integrated Project Teams (IPTs)
Mission Area & Agency Planning & Execution
NOTE: Final IT Governance Decision Authority resides with the Secretary
Enterprise Architecture
Advisory Council
Agency Investment Review Boards (IRB)
*Inclusion of EA in IPT discussions
Reference Models (EAVE)
IT Governance – Applicable Governance Boards
NEW

## Slide 45: Scoring Criteria V1.9: Cost Savings/Cost Avoidance
Scoring Criteria – Added to Performance Section
Notional Example of Investment Scoring
Scoring Criteria are associated with individual investments
MA IT Portfolio Score is scored against the number of Total Number of Initiatives associated with the Total number of Active Investments in the Portfolio (Eliminated Investments in PY are not included).
1
2
DATA
NEW

## Slide 46
IT Governance – Meeting Frequencies
Meeting Frequency | CIO Rating
Quarterly | 5
Semi - Annual | 4
Annual | 3
Over 12 Months | 2
Never | 1
As mentioned in the IT Governance category, USDA has five frequencies when applicable Governance Boards can meet & be reported on:
  Monthly
  Quarterly
  Semi-Annual
  Annual
  Never
See below table providing the IT Governance Category rating if Investment Managers can have their investments reviewed by the applicable governance boards and meet the additional IT Governance Category requirements. This is applicable to all Major & Standards in the department.
NEW

## Slide 47
Governance Requirements | Requirement Explanation | Examples of Satisfying Requirement
Investments and any key projects have been briefed, at a minimum of a monthly basis to the applicable Governance Boards & Applicable governance boards required for briefing. | All investments (Major, Non-Major, Standard) and their associated Key projects are required to be briefed and approved by their Mission Area governance board. In addition, Major investments and their associated Key projects are required to be briefed and approved at the Department’s Enterprise governance boards (IAB and E-Board). Note: See IT Governance Structure Slide | Governance briefings can be satisfied using several methods: “In-person governance” board meeting/briefing. “Virtual governance” board vote, do not require a meeting. Investment briefing and supporting documentation will be reviewed by governance board members who will provide a vote and associated action items/conditions in person or via email depending on method. Meetings (In-person or Virtual) can include multiple investments or multiple Key projects Virtual votes will need to be approved in advance, and governance board chair has the right to call “In-person meeting if deemed necessary.
“How to define Key projects”? What is the process for accomplishing or tracking these meetings? | Key projects are defined at the discretion of the Mission Area and their Investment Managers. Each Key project identified in AgMAX should also be a Key project in the Mission Area’s 5 year spend plan. The process for accomplishing these Governance meetings is also the responsibility of the Mission Area. Tracking of these Governance meetings will be in AgMax by the Capital Planning Liaison. | CPIC liaisons can assist Mission Areas with determining if projects should be considered “Key projects”. Each Mission Area’s governance board should be meeting on a reoccurring basis. Tracking and providing proof these meetings can be accomplished by upload any of the following documents to AgMAX prior to the 10th business day of the month. Meeting Minutes Signed Approval Memo Governance Board Briefing
NEW
IT Governance – Requirement Details and Examples

## Slide 48
 | Regular Governance | Virtual Governance (Via Email)
Governance Meeting Type and How IT Works? | Integrated Advisory Board (IAB) holds a meeting (in person or virtual). Investment manager will brief IAB IAB review, prioritize, and evaluate major and enterprise-wide IT investments (initiatives or projects). IAB votes/Action Items captured in person IAB Provides approval memo and recommendations. | Integrated Advisory Boards (IAB) receives briefing and supporting documentation via email. IAB members perform individual review, prioritization, and evaluation of major and enterprise-wide IT investments (initiatives or projects). IAB opportunity to ask questions. IAB vote / Action items are sent via email IAB Provides approval memo and recommendations.
What Governance Request Qualify? | Decision Gates 3-8 Portfolio Restructures Rebaselines Reprogramming Upgrades (Non- Major to Major) | Touchpoints (Annual or Incremental) Decision Gates 1&2 Downgrades (Major to Non-Major) Note: Virtual IAB reviews must be approved in advance.
Facilitation and Timelines | Final briefing and supporting documentation due 2 weeks prior to meeting. Signed IAB Memo 2 weeks after meeting. | After Virtual IAB is approved. Final briefing and supporting documentation due within 2 weeks. IAB members are allowed 2 weeks to review and ask questions. Signed IAB Memo 2 weeks after meeting. Note: CPIC liaison facilitates “Virtual Governance “meeting.
IT Governance – Enterprise Governance Meetings
NEW

## Slide 49
DME ACTIVITIES EXAMPLES | ACTIVITY DESCRIPTION
Authorization To Operate (ATO) Accreditation Costs | The costs associated with auditing and accreditation of new systems. The ATO represents the formal management approval to place a system into operation at USDA.
Commercial off-the-shelf (COTS) | Service or software available in the commercial marketplace that can be bought and used under government contract. For example, Microsoft and Salesforce.
Computer and IT-Related Hardware | Computer Hardware – includes components (internal) and peripherals (external). Computer hardware refers to the physical parts of a computer and related devices. Internal hardware devices include motherboards, hard drives, and RAM. External hardware devices include network equipment, monitors, keyboards, mice, printers, and scanners. Drones, unmanned aircraft, equipment used for IT related tasks or research, such as microscopes or aerial cameras.
Contracted Labor | Contracted labor costs for planning, development, acquisition, system integration, and direct project management, overhead support and cloud implementations and/or migrations. Note: Contractor support not directly related to system development, i.e. administrative support, is considered a non-system cost. If the support is new to the investment, the estimated cost should be entered in the Non-System DLCC table under the DME category in AgMax.
Enhancement/Operating System Upgrades | Expanding the capacity of an asset or otherwise upgrading it to serve needs different from or significantly greater than those originally intended. For example, replacement of a laptop with a newer model or adding a new functionality to an existing system. This is not considered a code fix.
Government Labor Costs | Labor cost (salaries and benefits) associated with government Full Time Equivalents (FTEs).
Implement Legislative or Regulatory Requirements | Presidential directives or legislative requirements, such as improving Section 508 compliance or cloud implementation.
Development, Modernization and Enhancement (DME) - DME refers to projects and activities leading to new IT assets/systems, as well as projects and activities that change or modify existing IT assets to improve capability or performance. Expanding the capacity of an asset or otherwise upgrading it to serve needs different from or significantly greater than those originally intended. (Source: Capital Planning Guidance). Examples of DME activities are listed but not limited to, the items shown in the table below:
Development, Modernization, and Enhancement (DME) - Definitions

## Slide 50
DME ACTIVITIES EXAMPLES | ACTIVITY DESCRIPTION
Database Restructuring | Performing structural changes to a database design. This includes minor or complex changes.
Software Functional Change | Implementing functional requirement changes to the application, such as UV/UX minor modifications, i.e. screen color changes, update to dates in forms. This includes minor or complex changes.
Software Development | Technology modernization for the purpose of adding capability or changing the performance or architecture of the end item is considered a modernization cost.
Software License Purchases | Purchasing of new or additional software licenses. Note: If the licenses have expired, the new purchase is considered DME and not an O&M licenses renewal cost.
Technology Refresh (Hardware/Software) | A Technology Refreshment is the intentional, incremental insertion of newer technology such as hardware or software, to improve the reliability, maintainability, to reduce cost, and/or enhance performance.
Development, Modernization, and Enhancement (DME) - Definitions

## Slide 51
Operations & Maintenance (O&M) - Operations & Maintenance Costs refers to the expenses required to operate and maintain an IT asset that is operating in a production environment. O&M costs include costs associated with operations, maintenance activities, and maintenance projects needed to sustain the IT asset at the current capability and performance levels. It includes Federal and contracted labor costs, corrective hardware and software maintenance, voice and data communications maintenance and service, replacement of broken or obsolete IT equipment, overhead costs, and costs for the disposal of an asset. Also commonly referred to as steady state. (OMB Capital Planning Guidance).
O&M ACTIVITIES EXAMPLES | ACTIVITY DESCRIPTION
ATO Reaccreditation Costs | The costs associated with auditing and reaccrediting a system in advance of an expiring Authority to Operate (ATO).
Code Fix/Patch | Debugging and fixing custom-developed software code that has a defect preventing the application system from satisfying its existing requirements. A patch, sometimes just called a fix, is a small piece of software that's used to correct a problem, usually called a bug, within an operating system or software program. The fix/patch does not include any new functions or enhancements.
Code Restructuring | Restructuring existing computer code - changing the factoring, possibly improving its internal logic without changing its external behavior. The restructuring does not include any new requirements or enhancements.
Data Maintenance | Developing scripted Data Modification Language (DML) or Structured Query Language (SQL) in order to manage the quality, growth, reliability, or maintainability of the data within the application database.
Hardware Maintenance Costs | The costs and labor associated with repairing or replacing defective, out-of-warranty, or near-out-of-warranty hardware in efforts to "keep the lights on" (KTLO).
IT Support/Training/ Management | Conduct training for IT applications, Help Desk support, participation in technology review boards, departmental CIO activities, CPIC, OMB Exhibit 300 reporting, Normal maintenance activities, such as performing backups, re-indexing databases, etc.
Software Renewal | The costs associated with renewing the same level of product maintenance support from a vendor for software products/licenses, or suite of products owned. Note: This maintenance/software renewal cost is for non-expired licenses or contracts. Any new efforts are considered DME.
Operations & Maintenance (O&M) - Definitions

## Slide 52
Operations & Maintenance Project Examples
Operations & Maintenance (O&M) Projects
Operations – “Keep the Lights On (KTLO)” technology refers to the portion of IT has to perform on daily operational tasks.
Predictive Maintenance – Type of maintenance that is carried out in order to anticipate possible failures and to try to avoid them before they occur.
Preventative Maintenance – Carried out in order to prevent possible failures and improve the functioning of a system.
Corrective Maintenance – Solution that must be applied when the predictive and preventive maintenance have not worked properly or when these have not been able to avoid the failure.
Evolutionary Maintenance – With evolutionary maintenance, we want to ensure that computer systems do not become obsolete, but remain updated in order to offer the users the best technology options, depending on the possibilities of each company and organization.
NEW

## Slide 53
It is recommended to have a consistent person or small group who determine all ROI calculations. It makes the numbers credible to the organization and eliminates huge swings in calculated returns/savings.
The Investment is, but not limited to, calculation of employee wages and benefits associated with the time devoted to the improvement activity; outside consulting costs; any supplies or materials; acquisition costs (office equipment, desks, software, etc.); and others.
The Return may come in many different forms, such as, but not limited to, measurements, metrics, actual data numbers, surveys, interviews, and perception.
EXAMPLE OF POTENTIAL BASELINE METRICS INCLUDE:
Reduction in the number of process steps
Greater employee or customer satisfaction
Providing enhanced or additional services
Cost avoidance/acquisition cost avoidance
Decrease backlog
Less rework
Return on Investment (ROI)
BEFORE – Training folders with paper documentation
AFTER – Documentation now in SharePoint and searchable
Notional

## Slide 54
CIO Rating weighted calculations for Major, Non-Major, Standard Investments | Weighted Score
Investment Overview | 10
Contract Acquisition Strategy | 10
Performance Rating | 15
Risk Management | 15
Project Management* | 15
FAC PPM Certification | 10
TBM | 10
IT Governance | 15
Total | 100
CIO RATING WEIGHTED CALCULATIONS
*Investment can not have a CIO rating higher than the Project Management category score.